## Roles & Tools
Role | Tool | Built Status
Molecular Biologist | Textbook | DONE
Molecular Biologist | Lab key | DONE
Security Agent | Flashlight | DONE
Security Agent | Gun | DONE
System Administrator | Password sheet | DONE
System Administrator | Alphanumeric keycard | DONE

## Supplies
Supply List Tracking
|  | Legend: | Not Required | Nice to have
|  |  | DONE | We have the item in DONE 2 state in Annie's office
|  |  | PROGRESS | Working on it
|  |  | HAVE | Items we have on site but need until day of event
|  |  | BRING | Items we have at home and need to bring in
|  |  | <blank> | No progress
Tool | Location | Status | Assigned | Details
Domain setup |  | DONE | Annie, Jeff | biocoretek.com on our shared hosting, pass: B!0C0r3+3k
Email account setup |  | DONE | Annie, Jeff | register@biocoretek.com on our shared hosting, pass: B!0C0r3+3k
Ad campaign 1 |  | DONE | Annie, Jeff
Ad campaign 2 |  | DONE | Annie, Jeff
Email to staff |  | DONE | Annie
Clue Card | All | DONE | Annie | 1 clue card, bring it to lobby
Out of game stickers | All | DONE | Annie
Protocol sound bite | All | PROGRESS | Jeff | ALARM "Lockdown in effect. Implement protocol KA-452."
Dead cards | All | DONE | Annie | On black paper, x7
Infected cards | All | DONE | Annie | On red paper, x7
String | All | DONE | Annie
Clear Tape | All | DONE | Annie
Tarp 1 / Mylar | Lobby | DONE | Jeff
Laptop for us to track | Lobby | HAVE | Annie | Annie's laptop
Lanyards 2x3 | Lobby | DONE | Annie | 2x3 job labels
Binder clips for lanyards | Lobby | DONE | Annie
Lab Key | Lobby | HAVE | Annie | Key to Annie's office
Lab Key label | Lobby | DONE | Annie
Textbook | Lobby | DONE | Jeremy
Flashlight | Lobby | DONE | Jeff, Jeremy
Password sheet | Lobby | DONE | Annie
Alphanumeric keycard | Lobby | DONE | Annie
Gun | Lobby | DONE | Annie
Doctor Lab Coat | Lobby | DONE | Annie
Tarp 2 | Hallway (Chubb's Office) | DONE | Annie
Facility Map Sign | Hallway (Chubb's Office) | DONE | Annie
Do not enter sign | Hallway (Chubb's Office) | DONE | Annie
Level 5 key (master) | Level 5 Back Door | HAVE | Steve | Steve's master key
Level 5 key label | Level 5 Back Door | DONE | Annie
Restricted area sign | Level 5 Back Door | DONE | Annie
Laptop for camera | Level 5 Back Door | DONE | Steve
Camera into restricted | Level 5 Back Door | DONE | Jeff
Speaker System | Level 5 Back Door | HAVE | Jeff
Ripped keycode half1 on door | Level 5 Back Door | DONE | Annie
Label for box with level 5 key | Level 5 Back Door | DONE | Annie
Lock Box with Level 5 key | Level 5 Back Door | DONE | Jeff | Needs to be lockable with 4 numbers
Red light bulb and stand | Medical Dispensary (Vic's Desk) | DONE | Annie | Flashing light for lockdown
Black Garbage bags | Medical Dispensary (Vic's Desk) | DONE | Annie | To cover lights
Tarp 3 | Medical Dispensary (Vic's Desk) | DONE | Annie
Antidote key ring | Medical Dispensary (Vic's Desk) | DONE | Annie
Antidote Cards | Medical Dispensary (Vic's Desk) | DONE | Annie | on yellow paper, x7
Servo mechanism | Medical Dispensary (Vic's Desk) | DONE | Jeremy
Servo container box | Medical Dispensary (Vic's Desk) | DONE | Jeff
Extra 9V batteries for arduino | Medical Dispensary (Vic's Desk) | DONE | Jeff | A few more extras in case it runs out
Antidote Box number sign | Medical Dispensary (Vic's Desk) | DONE | Annie
Antidote Dropper Case | Medical Dispensary (Vic's Desk) | PROGRESS | Jeff
Unlock antidote server | Medical Dispensary (Vic's Desk) | DONE | Jeremy | API to be called from unlock page
Tarp 4 | Medical Dispensary (Vic's Desk) | DONE | Annie
Desk Lamp | Level 5 Hallway | DONE | Annie | From Annie's office
Table | Level 5 Hallway | DONE | Jeff | Any kind of table structure, file cabinet is fine
Biohazard box with infection | Level 5 Hallway | DONE | Jeff | A closed but unlocked box containing an infection paper
Biohazard box label | Level 5 Hallway | DONE | Annie
Saran wrap for biohazard box | Level 5 Hallway | DONE | Annie | Enough to use for each game
Specimen jars | Level 5 Hallway | DONE | Jeff | With glow stick water
Do not enter sign | Hallway (Chubb's Office) | DONE | Annie
Timer Clock | Briefing Room (Quiet Room) | DONE | Jeff
Tablet for timer clock | Briefing Room (Quiet Room) | DONE | Jeff
Frame for timer tablet | Briefing Room (Quiet Room) | DONE | Jeff
Box IT junk | Briefing Room (Quiet Room) | DONE | Steve
Label for IT box | Briefing Room (Quiet Room) | DONE | Annie
Welcome manual x6 | Briefing Room (Quiet Room) | DONE | Annie
Step stool | Briefing Room (Quiet Room) | DONE | Annie
USB Keyboard | Briefing Room (Quiet Room) IT box | DONE | Steve | Will be a box of junk marked "IT Hardware"
PS/2 Keyboard | Briefing Room (Quiet Room) IT box | DONE | Steve | Will be a box of junk marked "IT Hardware"
Monitor with sticky | Briefing Room (Quiet Room) | DONE | Steve
Computer | Briefing Room (Quiet Room) | DONE | Steve | Username: Halloween DomainUsername: accounting-jma\halloween Password: Hostopia@123
USB hub/extension | Briefing Room (Quiet Room) | DONE | Steve
Login Webpage | Briefing Room (Quiet Room) | DONE | Annie
Project Webpage | Briefing Room (Quiet Room) | DONE | Annie
Unlock antidote webpage | Briefing Room (Quiet Room) | DONE | Annie
Recycle bin | Briefing Room (Quiet Room) | DONE | Annie
Official papers for recycle bin | Briefing Room (Quiet Room) | DONE | Annie
Ripped keycode half2 in recycle | Briefing Room (Quiet Room) | DONE | Annie
Doorstop in bin of IT stuff | Briefing Room (Quiet Room) IT box | DONE | Jeremy
Doctor Lab Coat | Briefing Room (Quiet Room) | DONE | Jeff
Name of Lab sign | Lab 5-E (Jeff's/Jeremy's Office) | DONE | Annie
Name of Lab sign | Lab 5-H (Derek's Office) | DONE | Annie
Name of Lab sign | Lab 5-G (Annie's Office) | DONE | Annie
Port Hole | Lab 5-G (Annie's Office) | DONE | Annie | w 16 1/4 in, h 4ft
Tarp 5 | Lab 5-G (Annie's Office) | DONE | Annie
Doctor Zombie | Lab 5-G (Annie's Office) | DONE | Jeremy | Has to be dressed as doctor zombie
Help Me paper to stick in port | Lab 5-G (Annie's Office) | DONE | Annie | Doctor Zombie to slap in window
White board w/ access code | Lab 5-G (Annie's Office) | DONE | Annie
Lab Equipment | Lab 5-G (Annie's Office) | DONE | Jeremy | Use what Derek has, get it from him, put in Annie's office
Contaminent tape over doorknob | Lab 5-G (Annie's Office) | DONE | Jeff | Deter people from opening the door right away
Bloody hands | Lab 5-G (Annie's Office) | DONE | Jeremy
Zombie Makeup | Lab 5-G (Annie's Office) | DONE | Jeremy | fake blood, hair spray color

## Puzzles
Puzzle | Location | Answer | Required Clue 1 | Required Clue 2
Protocol number | Anywhere | KA-452 | Audio playing on a loop
Med kit location name | Briefing Room | Medical Dispensary | Welcome package booklet
Med kit physical location | Hallway | Vic's Desk | Facility map on wall
Login page | Briefing Room |  | Turn on monitor
Project name | Briefing Room | caffeine | Molecule on login page | Textbook
Password | Briefing Room | 5F?-wpd%uH | Project name | Password sheet
Web app access | Briefing Room |  | Password | Keyboard
Web app unlock antidote | Briefing Room |  | Med kit box number | Med kit box password
Level 5 Daily Access Code | Level 5 Back Door | F1-C5-D3-J2 | Level 5 Back Door daily half1 code | Briefing Room daily half2 code
Level 5 Keybox password | Level 5 Back Door | X7F8 = 9738 | Level 5 full code | Alphanumeric keycard
Level 5 area key | Level 5 Back Door |  | Level 5 key from keybox
Med kit box password | Lab 5-G | 3176 | Flashlight
Lab entrance | Lab 5-G |  | Lab key
See into lab | Level 5 Hallway |  | Step stool
Med kit box number | Medical Dispensary | L5-4721 | Restricted area key

## Point System
Puzzle # | Puzzle | Positive Points Multiplier | Positive Points | Negative Points | Negative Points Multiplier | Notes
1 | Find Protocol - Goal |  | 5
2 | Open Monitor |  | 5
2 | Plug Keyboard |  | 5
2 | Figure out Project Name |  | 5
2 | Figure out Project Password |  | 5
2 | Login to Project Page |  | 10
3 | Find both Level 5 password halves |  | 5
3 | Unlock Level 5 keybox |  | 5
3 | Unlock Level 5 |  | 10
3 | Use Doorstop |  | 5
4 | Unlock Antidote |  | 25
| Give Antidote to Live Doctor |  | 10
| Exit uninfected before end time | 5 | 15 |  |  | Per person exited (includes Doctor), max 15 points (3 people)
| Anyone Becomes Infected |  |  | -15 | -5 | Per person infected anytime in game, max -15 points (3 people)
| Gun Shots Fired |  |  | -7 | -1 | Each bullet used, max 7 points (7 bullets)
| Total | 5 | 110 | -22 | -6
B | Minutes left to end time | 0.5 | 15 |  |  | For every whole minute left on the clock after your whole team exits (must be uninfected to exit)
| Bonus Total | 5 | 125 | -22 | -6

## Out of Game
List of locations for Out of Game Stickers
Location | Item | Status
Briefing Room (Quiet Room) | Box containing computer | DONE
Lab 5-H (Derek's Office) | Door Handle